## Sheet1
Type | Description | Task Dependency | Priority | Status | Estimate
Epic 1 | Develop DRMS web-based command center application which provides tools to visualize real-time data from IoT Sensors and field reports through dashboards and heatmaps. |  | Highest
User Story | As an admin I can view dashboard and heatmaps to visualize data from IoT sensors
Task 1 | Create front-end design to view and search for IoT Sensors and make sure the search is easily accessible, and there is space for priority sensors as well as recently checked sensors |  | Medium |  | 20
Task 2 | Implement front-end design to view and search for IoT Sensors | Task 1 | High
Task 3 | Create front-end design for the dashboards and heatmaps of IoT Sensors page and make sure that they are placed next to each other horizontally and easy to access |  | High |  | 20
Task 4 | Implement the front-end design for the dashboards and heatmaps of IoT Sensors page | Task 3 | High
Task 5 | Implement the back-end to easily go back from the sensor page to the sensor details page (where you view heatmaps and dashboards) as well as for checking that sensor data. | Task 2 & 4 | High |  | 20
Task 6 | Sync the sensor data to the sensor UI and add locations of the sensors below them |  | High
Test Case | Test that the sensor data is correctly synced and the sensor locations are correct | Task 6 | High |  | 30
User Story | As an admin, I can use the web app to deploy rescue teams |  | High
Task 7 | Make the user interface for deploying rescue teams that appears when hovering over the location |  | High |  | 20
Task 8 | Make the deploy rescue team to location button dial the rescue team closest to that location | Task 7 | High
Test Case | Test if the correct rescue team is called when pressing the deploy rescue team to location button | Task 8 | Medium
Epic 2 | Make the mobile application for on-ground observers that allows them to quickly report incidents and communicate with the central command center. The app should also send them disaster alerts. |  | High
User Story | As the on-ground responder using the mobile app, I am able to intuitively use the UI to quickly report incidents and message the command center so they can deploy rescue teams.
Task 9 | Design and implement the front-end user interface that has current location, disasters in current location, a dedicated place where disaster alerts appear. |  | High
Task 10 | Design and implement the front-end user interface for communicating with the command center |  | High
Task 11 | Implement the back-end for the front-ends described in tasks 9 and 10; current location needs to update and include address as well as country and city or town, etc. | Task 9 & 10 | High |  | 20
Test Case | Test if the admin using the command center can instantly receive on-ground user messages | Task 11 | Medium |  | 40
Test Case | Test if the user interface is intuitive with clients | Task 9 & 10 | Medium |  | 30